## Slide 1: Ventilation Systems Capital Asset Projects Safety Significant Confinement Ventilation System (15-D-411) Exhaust Shaft (15-D-412)
Ronald E. Gill
Acting Federal Project Director / Operations Activity Manager
Carlsbad Field Office
Office of Environmental Management
February 19, 2016

## Slide 2: Project Management Background
DOE Order 413.3B “Program and Project Management for the Acquisition of Capital Assets”
  Disciplined approach for acquiring capital assets
  Project goes through “Critical Decisions (CD)” during the development and approval of the project
  Many independent reviews by other organizations to ensure acquired asset will meet the mission need
Secretary of Energy Memorandum December 2014 “Improving the Department’s Management of Projects”
  Additional review requirements
  Independent Analysis of Alternatives to General Accounting Office standards
  Additional design maturity requirements for Hazard Category 2 Nuclear Facility at CD-2

## Slide 3: Critical Decision (CD) Process
Line Item Funding
Base Funding
Base Funding
Oct. 24, 2014
Dec. 23, 2015

## Slide 4: Critical Decision 1 – Approve Alternative Selection and Cost Range
CD-1 documentation and reviews consisted of the following:
  Acquisition Strategy
  Preliminary Project Execution Plan
  Tailoring Strategy
  Independent Analysis of Alternatives
  Independent Cost Review
  Independent Project Review
  Conceptual Design Report / Conceptual Safety Validation Report
  Conceptual Safety Design Report
  National Environmental Policy Act Strategy

## Slide 5: Analysis of Alternatives
Nuclear Waste Partnership (NWP) proposed a total of 24 alternatives with 2 requiring additional study through Conceptual Design
  Alternative 1-A
    Provide a new unfiltered exhaust shaft for mining operations and use existing exhaust shaft with additional filtration capacity for full waste handling and disposal operations
  Alternative 1-D
    Existing exhaust shaft with filtered ventilation sufficient for full mining and waste handling and disposal operations
An Independent Analysis of Alternatives was contracted with Trinity Engineering Associates that developed 4 alternatives that were similar to the ones developed by NWP

## Slide 6: Approval of CD-1
Approved Acquisition Strategy
Approved Preliminary Project Execution Plan
Approved Tailoring Strategy that combined CD-2 and CD-3
Alternative 1-A selected with two projects, cost ranges, and proposed CD schedule
  Safety Significant Confinement Ventilation System (15-D-411)
    Use existing exhaust shaft with additional filtration capacity for waste handling and disposal operations
    $189M to $280M
  Exhaust Shaft (15-D-412)
    New unfiltered exhaust shaft for mining operations
    $81M to $118M

## Slide 7: Path Forward
Design Request for Proposal on the two projects
Design in Fiscal Year 2016, completion in Fiscal Year 2017
Long Lead Procurements in Fiscal Year 2017
  Salt Removal Systems
  Exhaust Fans
  Filter Housings
  Diesel Standby Generators